## Advanced AssumptionConstraint S
ID | Name of the Project | Type | Assumption/Constraint | Status | Category | Description | related docs & elements | Risk Register ID | Benefit ID | Comments | review frequency | last review date | Changed by | Change date | Created by | Creation date
1 | Artificial Intelligence | Assumption | Project is based on current environment | verified as correct | Category A - Environmental | Project requirements are based on current environment with respect to public infrastructure and safety. | Artificial Intelligence SOW | AI-04 | AI-05 | The environment needs to be evaluated on a regular interval for new trends in the market. | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
2 | Artificial Intelligence | Assumption | Availability of tools and equipment | verification in process | Category A - Environmental | All tools, equipment, and environment for development of AI capability will be available. | Artificial Intelligence SOW | AI-07 | AI-03 | Resource assessment needs to be completed periodically. | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
3 | Artificial Intelligence | Assumption | AI will be supported by all applicable vehicle components | verified as correct | Category B - Technical | A comprehensive integration effort across all applicable vehicle components will be supported. | Artificial Intelligence SOW | AI-08 | AI-04 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
4 | Artificial Intelligence | Assumption | Anticipated changes in government regulations | verification in process | Category C - Political | Since self-driving vehicles shall be sold in huge quantities and shall be new to the market, changes in regulations are anticipated. | Artificial Intelligence SOW | AI-04 | AI-06 | -A check on automobile regulations needs to be executed | Bi-weekly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
5 | Artificial Intelligence | Constraint | Limited to the available public infrastructure and regulations | not verified yet | Category A - Environmental | AI for self-driving vehicles will be tailored to current public infrastructure – roadways, traffic signals, etc. and regulations. | Artificial Intelligence SOW | AI-04 | AI-04 | Although no regular review is required, updates need to be made regularly | Once the AI is setup according to public regulations, it does not require to be reviewed again | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
6 | Artificial Intelligence | Constraint | Scope is defined by government's self-driving automobile's safety requirements | verification in process | Category C - Political | Public law and regulation regarding self-driving vehicles will define the scope of AI project and technology requirements. | Artificial Intelligence SOW | AI-02 | AI-03 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
7 | Artificial Intelligence | Constraint | Design and Integration will introduce AI constraints. | verification in process | Category B - Technical | AI will require continuous interaction in design, integration and testing with vehicles and vehicle technologies and components. Integration will introduce AI design constraints. | Artificial Intelligence SOW |  |  |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
8 | Artificial Intelligence | Assumption | Funding is available and project is not cancelled/delayed | verification in process | Category A - Environmental |  | Artificial Intelligence SOW | AI-01 | AI-01 | Assumption based on risk | not required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
9 | Artificial Intelligence | Assumption | AI technology will be available for integration into self-driving vehicle system. | verification in process | Category B - Technical |  | Artificial Intelligence SOW | AI-02 | AI-04 | Assumption based on risk | not required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
10 | Artificial Intelligence | Assumption | No technical difficulties in AI development or implementation will delay planned project outcome. | verification in process | Category B - Technical |  | Artificial Intelligence SOW | AI-03 | AI-05 | Assumption based on risk | not required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
11 | Artificial Intelligence | Assumption | The changes in safety, vehicle, traffic regulations will not affect project deliverables/requirements. | verified as correct | Category C - Political |  | Artificial Intelligence SOW | AI-04 | AI-03 | Assumption based on risk | not required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
12 | Artificial Intelligence | Assumption | There will not be any AI failures that could contribute or cause vehicle accidents. | verification in process | Category B - Technical |  | Artificial Intelligence SOW | AI-05 | AI-04 | Assumption based on risk | Daily | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
13 | Artificial Intelligence | Assumption | Secure from cyberattacks. | verification in process | Category B - Technical | Cyberattacks will not compromise the AI system. | Artificial Intelligence SOW | AI-06 | AI-05 | Assumption based on risk | Daily | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
14 | 3D Parts Printing | Constraint | New government regulation making it harder or impossible to use 3D printed parts in vehicles. | verification in process | Category B - Technical | New regulations would mean reimplementations that take time | 3D Parts Printing SOW | 3DP-05 | 3DP-05 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
15 | 3D Parts Printing | Constraint | 3D Parts Printing is not at the advanced level needed for the project | verified as correct | Category B - Technical | Market shall take more time to consider 3D Parts Printing at a more complex level. | 3D Parts Printing SOW | 3DP-01 | 3DP-01 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
16 | 3D Parts Printing | Assumption | Consumers make their choice of purchasing a vehicle on maintenance costs after the purchase. | verification in process | Category A - Environmental |  | 3D Parts Printing SOW | 3DP-06 | 3DP-04 |  | Not required, surveys available on the global network | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
17 | 3D Parts Printing | Assumption | VW can repair a reputation that has been heavily damaged in the recent past. | verified as correct | Category A - Environmental |  | 3D Parts Printing SOW | 3DP -06 | 3DP-05 | As per previous situations VW has emerged from. | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
18 | 3D Parts Printing | Assumption | An advanced just in time inventory system that 3D Parts Printing would essentially create will produce real cost savings. | verification in process | Category D - Financial | JIT inventory costs will in the future produce cost savings since materials, tools and equipment shall be available in time | 3D Parts Printing SOW | 3DP-07 | 3DP-02 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
19 | 3D Parts Printing | Assumption | Technology will be able to produce parts up to safety standards. | verified as correct | Category B - Technical |  | 3D Parts Printing SOW | 3DP-01 | 3DP-05 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
20 | 3D Parts Printing | Assumption | The cost of developing and manufacturing a 3D printer will allow VW to have a positive ROI on the project. | verification in process | Category D - Financial | The relation between investing into 3D Parts Printing will in turn reduce operational and logistics costs, since the automobile parts shall be manufactured at VW. | 3D Parts Printing SOW | 3DP-02 | 3DP-03 | Continuous financial monitoring is required to maintain costs | Regularly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
21 | 3D Parts Printing | Assumption | No lack of quality in printed parts | verification in process | Category B - Technical |  | 3D Parts Printing SOW | 3DP-03 | 3DP-05 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
22 | 3D Parts Printing | Assumption | Higher speed in introducing to market and have competition advantage | verification in process | Category A - Environmental |  | 3D Parts Printing SOW | 3DP-04 | 3DP-05 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
23 | Brain Computer Interface | Constraint | Total amount of global knowledge in this area is low | not verified yet | Category A - Environmental | Since the knowledge about brain computer interface is low in the market at present, the growth of this project is dependent on the acceptance of the new tool by the consumers. | Brain Computer Interface SOW | BCI-01 | BCI-03 |  | Not required, surveys available on the global network | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
24 | Brain Computer Interface | Constraint | Cost of the materials decided by the management. | verified as correct | Category D - Financial |  | Brain Computer Interface SOW | BCI-02 | BCI-02 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
25 | Brain Computer Interface | Constraint | Cost of the automotive and neural machinery decided by the management. | verified as correct | Category D - Financial |  | Brain Computer Interface SOW | BCI-01 | BCI-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
26 | Brain Computer Interface | Constraint | Assigned budget to the project by the management. | verified as correct | Category D - Financial | Limited to the amount given for this project. | Brain Computer Interface SOW | BCI-07 | BCI-01 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
27 | Brain Computer Interface | Constraint | Time for the develop of the design and fabrication | verified as correct | Category E - Internal | Limited to the time given for this project. | Brain Computer Interface SOW | BCI-02 | BCI-02 |  | Daily | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
28 | Brain Computer Interface | Constraint | Permits for the non-human and animal tests | verified as correct | Category C - Political | Non-human and animals test permits are acquired for the security and compliance of this project. | Brain Computer Interface SOW | BCI-06 | BCI-03 |  | Once the permits are followed, review needs to be done only upon any changes in the permits. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
29 | Brain Computer Interface | Constraint | Permits for the human tests | verified as correct | Category C - Political | Human test permits are acquired for the security and compliance of this project. | Brain Computer Interface SOW | BCI-06 | BCI-03 |  | Once the permits are followed, review needs to be done only upon any changes in the permits. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
30 | Brain Computer Interface | Assumption | The knowledge in this area will significantly increase. | verification in process | Category A - Environmental |  | Brain Computer Interface SOW | BCI-01 | BCI-02 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
31 | Brain Computer Interface | Assumption | The market size will increase in the next years, for side applications too. | verification in process | Category A - Environmental |  | Brain Computer Interface SOW | BCI-02 | BCI-01 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
32 | Brain Computer Interface | Assumption | Data analyst skills will be enough to interpret the neural data. | verification in process | Category B - Technical | To develop trends and usage statistics considering all related factors | Brain Computer Interface SOW | BCI-01 | BCI-03 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
33 | Brain Computer Interface | Assumption | Leakage of information will be controlled and competitors will be monitored. | verification in process | Category E - Internal | Higher security and risk management features will be installed considering the high risk in this project. | Brain Computer Interface SOW | BCI-07 | BCI-02 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
34 | Brain Computer Interface | Assumption | A dedicated research team will be created in the future. | verification in process | Category E - Internal | For researching the new tools, techniques and implementation methodologies | Brain Computer Interface SOW | BCI-02 | BCI-01 |  | Once created, no monitoring is required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
35 | Brain Computer Interface | Assumption | Creation of partnership or potential acquisition of the Neural division in the future. | verification in process | Category B - Technical |  | Brain Computer Interface SOW | BCI-06 | BCI-01 | For funding/sponsoring purposes | Once created, no monitoring is required | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
36 | Augmented Reality | Constraint | Technological constraint related to AR dashboards | verified as correct | Category B - Technical | Augmented Reality Dashboard dashboards can only be as good as the hardware and software technology allow them to be. | Augmented Reality Dashboard SOW | ARD-04 | BCI-02 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
37 | Augmented Reality | Constraint | Safety considerations | verification in process | Category A - Environmental | This project must take into consideration all security and damage prevention aspects | Augmented Reality Dashboard SOW | ARD-05 | ARD-01 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
38 | Augmented Reality | Constraint | There are also legal and regulatory constraints that restrict our freedom of action. | verified as correct | Category C - Political | Public law and regulation regarding augemented reality will define the scope of this project and technology requirements. | Augmented Reality Dashboard SOW | ARD-01 | ARD-04 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
39 | Augmented Reality | Constraint | Timeline constraint set by the management. | verified as correct | Category E - Internal | This must be rolled out by the end of the year. | Augmented Reality Dashboard SOW | ARD- 02 | ARD- 01 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
40 | Augmented Reality | Constraint | Research and Development in the market which change the approach to this concept | verification in process | Category A - Environmental | Unanticipated issues could slow down production more than we expect. | Augmented Reality Dashboard SOW | ARD- 03 | ARD- 03 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
41 | Augmented Reality | Assumption | Consumers will love this technology | not verified yet | Category A - Environmental | Only if the consumers like this technology will there be more sales eventually. | Augmented Reality Dashboard SOW | ARD-04 | ARD-04 | Analysis of the statistics of sales vs. new technology introduced is required to determine the success of this project | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
42 | Augmented Reality | Assumption | We will be the first to do it and will get a competitive advantage. | verification in process | Category A - Environmental | To gain competitive advantage over our competitors. | Augmented Reality Dashboard SOW | ARD-05 | ARD-02 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
43 | Augmented Reality | Assumption | The dashboard projection will be properly designed. | verification in process | Category B - Technical | It will not prove a distraction for drivers nor increase accident rate. | Augmented Reality Dashboard SOW | ARD-01 | ARD-01 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
44 | Augmented Reality | Assumption | There will not be technical difficulties that will delay product offering. | verified as correct | Category B - Technical |  | Augmented Reality Dashboard SOW | ARD- 02 | ARD- 02 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
45 | Augmented Reality | Assumption | Funding is available and is not reduced for any reason. | verified as correct | Category E - Internal | The project resources will not be reduced, the project will not be delayed or cancelled due to unavailable funding. | Augmented Reality Dashboard SOW | ARD- 03 | ARD- 03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
46 | Virtual Reality Retail Experience | Constraint | This project covers an application that can only be operated on a mobile operating system. It does not cover PC – Windows/MAC/Linux, etc. | verified as correct | Category B - Technical |  | Virtual Reality Retail Experience SOW | VRR-04 | VRR-03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
47 | Virtual Reality Retail Experience | Constraint | The application does not work without the VR headsets. Hence, the customer cannot experience virtual shopping at home until they purchase a VR headset. | verified as correct | Category B - Technical |  | Virtual Reality Retail Experience SOW | VRR-05 | VRR-05 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
48 | Virtual Reality Retail Experience | Constraint | Time constraint on building this innovative technological tool, since others in competition might achieve this edge sooner. | verification in process | Category A - Environmental |  | Virtual Reality Retail Experience SOW | VRR-04 | VRR-04 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
49 | Virtual Reality Retail Experience | Constraint | VR may still be too costly for many consumers. | verified as correct | Category D - Financial |  | Virtual Reality Retail Experience SOW | VRR-05 | VRR-05 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
50 | Virtual Reality Retail Experience | Assumption | Although the VR industry is still in the early stages, its annual revenue is forecasted to grow from less than $1 billion to $30 billion by 2020, per an advisory firm Digi-Capital. | verification in process | Category A - Environmental |  | Virtual Reality Retail Experience SOW | VRR-03 | VRR-07 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
51 | Virtual Reality Retail Experience | Assumption | Annual sales of headsets could hit half a billion by 2025. | verification in process | Category D - Financial |  | Virtual Reality Retail Experience SOW | VRR-04 | VRR-08 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
52 | Virtual Reality Retail Experience | Assumption | Technological advancements in VR hardware will keep pace with performance and cost demands. | verification in process | Category E - Internal |  | Virtual Reality Retail Experience SOW | VRR-01 | VRR-01 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
53 | Virtual Reality Retail Experience | Assumption | Highest security installed for this feature so that cyberattacks would not compromise VR system | verification in process | Category B - Technical |  | Virtual Reality Retail Experience SOW | VRR-02 | VRR-02 |  | Daily | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
54 | Virtual Reality Retail Experience | Assumption | Available to customers | verification in process | Category A - Environmental | Assuming customers will buy VR headsets. | Virtual Reality Retail Experience SOW | VRR-03 | VRR-08 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
55 | Virtual Reality Retail Experience | Assumption | Useful to customers | verification in process | Category A - Environmental | If VR service meets the needs of customers, project benefit will be realized and optimal usage of resources. | Virtual Reality Retail Experience SOW | VRR-04 | VRR-04 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
56 | Virtual Reality Retail Experience | Assumption | Positive customer experience | verification in process | Category A - Environmental |  | Virtual Reality Retail Experience SOW | VRR-05 | VRR-05 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
57 | Virtual Reality Retail Experience | Assumption | Technically not challenging for internal employees. | verification in process | Category B - Technical | The technology proves too difficult to use, or is unrealialbe, then product will be introduced with training and will then be used. | Virtual Reality Retail Experience SOW | VRR-06 | VRR-06 |  | Monthly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
58 | Smart Monitoring System | Assumption | Fuel Efficiency | verification in process | Category A - Environmental | Gas will remain a required resource for vehicle operation | Smart Monitoring System SOW | SMS-04 | SMS-03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
59 | Smart Monitoring System | Assumption | Fuel Efficiency | verification in process | Category A - Environmental | Gas will remain a non-renewable resource and viewed as precious | Smart Monitoring System SOW | SMS-04 | SMS-03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
60 | Smart Monitoring System | Assumption | Fuel Efficiency | verification in process | Category A - Environmental | Gas prices will not decrease, reducing the need for fuel efficiency | Smart Monitoring System SOW | SMS-04 | SMS-03 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
61 | Smart Monitoring System | Assumption | Fuel Efficiency | not verified yet | Category A - Environmental | A driver will follow suggested driving tips to improve fuel efficiency | Smart Monitoring System SOW | SMS-03 | SMS-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
62 | Smart Monitoring System | Assumption | Fuel Efficiency | not verified yet | Category A - Environmental | A driver drives an average of 15000 miles/year | Smart Monitoring System SOW | SMS-04 | SMS-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
63 | Smart Monitoring System | Assumption | Fuel Efficiency | verified as correct | Category D - Financial | The average price of gas is $3.00 /gallon | Smart Monitoring System SOW | SMS-04 | SMS-02 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
64 | Smart Monitoring System | Assumption | Fuel Efficiency | verified as correct | Category D - Financial | The average annual vehicle maintenance cost is $1,200 | Smart Monitoring System SOW | SMS-04 | SMS-01 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
65 | Smart Monitoring System | Assumption | Vehicle Maintenance | verified as correct | Category B - Technical | Car technology will not improve to the point where vehicle maintenance will not be necessary. | Smart Monitoring System SOW | SMS-05 | SMS-04 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
66 | Smart Monitoring System | Assumption | Vehicle Maintenance | not verified yet | Category A - Environmental | A driver will follow suggested vehicle maintenance requests | Smart Monitoring System SOW | SMS-05 | SMS-02 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
67 | Smart Monitoring System | Assumption | Safety | verification in process | Category B - Technical | Car technology will not improve to the point where accidents are no longer an issue. | Smart Monitoring System SOW | SMS-05 | SMS-04 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
68 | Smart Monitoring System | Assumption | Safety | not verified yet | Category A - Environmental | A driver will follow suggested driving tips to improve safety | Smart Monitoring System SOW | SMS-05 | SMS-02 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
69 | Smart Monitoring System | Assumption | Other | verification in process | Category A - Environmental | Internet and smartphone technology will not be obsolete in the future. | Smart Monitoring System SOW | SMS-05 | SMS-02 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
70 | Smart Monitoring System | Assumption | Other | verification in process | Category A - Environmental | Customers will be accepting of sharing car data with Volkswagen such as vehicle usage statistics and car location. | Smart Monitoring System SOW | SMS-01 | SMS-04 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
71 | Smart Monitoring System | Constraint | The technology will only be available for new VW vehicles | verified as correct | Category B - Technical |  | Smart Monitoring System SOW | SMS-02 | SMS-03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
72 | Smart Monitoring System | Constraint | The customer must have access to internet and smartphone technology | verification in process | Category B - Technical |  | Smart Monitoring System SOW | SMS-05 | SMS-01 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
73 | Smart Monitoring System | Constraint | Fuel efficiency can only improve a finite amount without improving vehicle components | verified as correct | Category A - Environmental |  | Smart Monitoring System SOW | SMS-01 | SMS-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
74 | Smart Monitoring System | Constraint | The system cannot prevent accidents, only help reduce risk | verified as correct | Category B - Technical | The project will deploy the highest of security and risk coverage for the safety of VWs consumers. | Smart Monitoring System SOW | SMS-02 | SMS-02 |  | Daily | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
75 | Web-Based Collaboration Application | Assumption | Employees will accept and embrace the new technology. | verification in process | Category E - Internal |  | Web-Based Collaboration Application SOW | WCS-04 | WCS-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
76 | Web-Based Collaboration Application | Assumption | Employees will learn the application thoroughly. | verification in process | Category E - Internal |  | Web-Based Collaboration Application SOW | WCS-03 | WCS-03 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
77 | Web-Based Collaboration Application | Assumption | Employees will make full use of application and use it for intended purpose. | verification in process | Category E - Internal |  | Web-Based Collaboration Application SOW | WCS-02 | WCS-01 |  | Half-yearly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
78 | Web-Based Collaboration Application | Assumption | Company will not implement other application for collaboration. | not verified yet | Category B - Technical | To protect company data and maintain integration. | Web-Based Collaboration Application SOW | WCS-02 | WCS-03 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
79 | Web-Based Collaboration Application | Assumption | Using this web based application would improve the work efficiency. | not verified yet | Category E - Internal | It is directly connected to employee job satisfaction and lesser attrition rates. | Web-Based Collaboration Application SOW | WCS-05 | WCS-02 |  | Annually | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
80 | Web-Based Collaboration Application | Constraint | Project has to be implemented in the allocated budget and time. | verified as correct | Category D - Financial | As per the management | Web-Based Collaboration Application SOW | WCS-04 | WCS-01 |  | Quarterly | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
81 | Web-Based Collaboration Application | Constraint | As it is a web based application a working network connection is required, employee cannot use it in offline mode. | verified as correct | Category B - Technical |  | Web-Based Collaboration Application SOW | WCS-03 | WCS-01 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
82 | Web-Based Collaboration Application | Constraint | Limited resources to provide training on the new application. | verified as correct | Category B - Technical |  | Web-Based Collaboration Application SOW | WCS-02 | WCS-02 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30
83 | Web-Based Collaboration Application | Constraint | Limited resource for supporting users like support team to resolve user queries, may lead to poor service. | verified as correct | Category B - Technical | The more time and effort required to maintain this employee portal, the less efficient it gets. Hence the constraint is dealt with good support program and automatic maintenance. | Web-Based Collaboration Application SOW | WCS-01 | WCS-03 |  | Done. No review required. | 2017-04-30 | Project Manager | 2017-04-30 | Project Manager | 2017-04-30

## Master Data
Assumptions & Constraints Log (template)
Project: | add project name here
Project Manager: | add project manager name here
Document Owner: | add document owner name here
Document Creation Date: | add document creation date here
Last Document Change Date: | add last document change date here
Last changed by: | add name of last person who changed the document here
Confidentiality level: | add confidentiality level here if relevant (public use/confidential/secret/...)
Authorized to read: | list stakeholders (groups) authorized to read this document here
Authorized to change (besides the document owner): | list stakeholders (groups) authorized to change this document here
Versioning scheme: | add information regarding document versioning scheme here
Review frequency of document: | add frequency of document reviews here
Master document storage place: | add storage place of master document (source of truth!) here
Approval for new version needed (name): | add information regarding approval process here
Publication procedure for new document version: | add information regarding publication procedure here

## Ranges
Assumption Status Range | Category Range | Type
not verified yet | Category A | Assumption
verification in process | Category B | Constraint
verified as correct | Category C
verified as incorrect

## Simple AssumptionConstraint She
ID | Type | Assumption/Constraint | Status | Description | Comments
1 | Assumption | Example data: ERP Release 6.1 will be available for public usage on the 1st of December 2014. | verification in process | If ERP release 6.1 is not available by 1st of January 2015 latest, then project has to start with release 6.0 and adapt the project plan via a change request which includes rework the project plan and update of the estimate. Probably this will add two months to the project timeline. | New contact at ERP vendor will be contacted to verify release schedule.
2 | Assumption | Example data: Business analyst Bob Allen will be available for the project 60% of his time (0.6 FTE) during the course of the whole project. | verified as correct | Bob Allen is the most knowledgeable business analyst regarding the new ERP system. If he is not available for at least 60% throughout the whole project, then he has to be replaced by another less skilled BA, which makes it necessary to review and update the BA-related project estimate.lines. | Bob's Manager has confirmed his availability throughout the project (at least 60%, probably up to 80%)
3 | Assumption | Example data: Project reporting will be managed by the division PMO, thus no project-specific project office resource has been budgeted. | verified as incorrect | Project need a project office resource and division PMO has stated that they have sufficient resources available to execute project reporting tasks without additional costs for the project. Thus no project specific project office resource has been budgeted. | Division PMO has no resources available. Thus project office resource has to be budgeted. Budget update not done yet!
4 | Constraint | Example data: Test team will not be available before 1st of July 2015. | not verified yet | Development will be done by end of May 2015 and the project could save some time and idle time, if the test team could start immediately beginning of June 2015. Unfortunately management has mentioned, that the test team is engaged with another project until end of June 2015 and thus only be available beginning of July 2015. | Situation will be verified by project manager with senior management end of Q1/2014!
5 | Constraint | Example data: Lowest cost bidder on PMIS system cannot be used, because company is not on the preferred vendor list. | verified as incorrect | Lowest cost bidder matching the minimum PMIS requirements cannot be selected due to procurement rules (not on preferred vendor list). Thus we have the 2nd bidder, which will increase PMIS related cost by 20%. | Lowest cost bidder has been added to preferred vendor list. Update of project cost estimate in progress (PMIS-related cost drop by 20%)
TEST DATA ENDS HERE (Please remove all previous lines including this before using this sheet!)

## Template Guide & Instructions
Guide to the Assumptions & Constraints Log Template
1. Take key decisions on document management & update sheet "Master Data" accordingly - What is the confidentiality level of the document? Who is authorized to read the document? Does the document have to be password-protected? - Who will be the document owner? Who is authorized to update the document apart from the document owner (if any)? - What is the planned frequency of document reviews & updates? - Where will the document be stored? - How will versions be marked (date in file name or version number in file name or...)? - Do new document versions have to be approved before publication? If yes, by whom? - How will new versions of the document be published and the stakeholder community be informed about a new version?
2. Take decisions on master data for this document & update tab "Ranges" accordingly! - What assumption/constraint status do you want to use in managing the assumptions and constraints? - What categories do you want to use for the assumptions and constraints?
3. Decide if you want to use the simple or advanced version of the assumptions & constraints sheet! - If in doubt start with the simple version. You can change later easily to the advanced version via copy & paste if there is a compelling reason to use the additional columns. Especially at project start the focus should be on managing the constraints and assumptions and not on managing the document! Start simple and stay simple as long as possible!
4. Remove example data from simple or advanced version of the assumptions & constraints sheet!
5. Start populating the simple or advanced sheet: - ID ==> mandatory ==> used to identify an item in the list, but you can use your own ID scheme. To start simple you can count up from one. - type ==> mandatory (valuerange) ==> defines if the item is an assumption or constraint - assumption/constraint ==> mandatory ==> describes the assumption/constraint with a few words (long form description should go into the description field) - status ==> mandatory (value range) ==> should indicate the status of the item (not verified yet/verified as correct/verified as incorrect/...) - category (only in advanced sheet) ==> optional (value range) ==> categorization of assumption/constraint (technical area/project phase/PM area/...) - description ==> optional, but recommended ==> extended description of the item (only in simple sheet: should mention documents and artifacts which are related to the assumption/constraint and might have to be reviewed and updated if there is a change to the assumption/constraint and especially if an assumption has been verified as incorrect!) - related documents & artifacts (only in advanced sheet) ==> optional ==> list of all documents and artifacts that are related to this assumption/constraint and need to be reviewed and updated if there is a change to the assumption/constraint (be as specific as possible, use hyperlinks if possible) - Comments ==> optional ==> any additional information regarding the item, which is not a description - review frequency (only in advanced sheet) ==> optional ==> state if there is a review frequency planned for this particular item which is different than the review frequency of the whole document (weekly/bi-weekly/monthly/quarterly/...) - last review date (only in advanced sheet) ==> optional ==> date of last review if the status and content of the item is still up to date (even if there is no change) - Changed by (only in advanced sheet) ==> optional ==> date of the last change to this item (no matter what of the fields was change) - Change date (only in advanced sheet) ==> optional ==> person who did the last change of this item - Created by (only in advanced sheet) ==> optional ==> date when this item was added to the list initially - Creation date (only in advanced sheet) ==> optional ==> person who created this item
6. Review and update list as stated in the review cycle stated on the master data sheet (or in the column review frequency if you use the advanced sheet)! - Especially if you change an assumption status to "verified as incorrect" you should review the related documents and artifacts accordingly to reflect this. - If you verify an assumption as incorrect or add a constraint which have no effect at all on any document or artifact then that assumption and artifact is actually obsolete.