## Instructions
Purpose of Benefit Register
The purpose of a program or project is to deliver change in an organized, planned structure. For change to be effective, benefit(s) must be identified, managed, and realized for the deliverable(s) and change(s) to be justified and accepted. The benefit register is an up to date list of planned benefits, who is responsible for measuring them, when they are expected to be realized, how they will be measured, baseline and current measurements, et cetera. The benefits in the register should encompass the reason for doing the program/project and justify the time and expense of making the change. Realization of the benefits listed in the register form a critical aspect of measuring program/project success.
Benefit Register Participants and Audience
Input into the benefit register may come from many different sources including, but not limited to, Sponsor, senior leadership, program/project intake form and/or business case, organizational and/or business unit strategic plans and initiatives, existing documentation, subject matter experts within business unit(s), and other stakeholders (such as staff, students, faculty).
The author and maintainer is the Program/Project Manager. Changes to benefits should be authorized through a formal Change Request by the Sponsor.
Instructions
1. Research and understand program/project information by reading any prior documentation (such as intake form(s), business case(s), and research/analysis) and speaking to Sponsor and other stakeholders. Identify why the program/project is being approved, what the expectations are for the final results, and what would make the deliverable(s) successful in the eyes of the sponsor and other stakeholders. These types of questions will help identify the benefits, which will sometimes be tied to business strategies/goals/objectives. Benefits, whether tangible or intangible, must be measurable.
2. Enter benefits in the benefit register with input from applicable stakeholders and Sponsor by filling out the applicable sections in the spreadsheet. The green italic text provides an example of a benefit and may be removed. See the Definitions page for a further description of each column on the spreadsheet, as well as valid values.
3. Update the document, as required, to reflect approved benefit changes as the program/project evolves.
4. Execute benefit measurements as outlined in register, recording actual results appropriately.
5. Upload to the Knowledge Base
Next Steps
Execute and document the benefit measurements according to the information laid out in this document. Update this document to reflect any approved changes during program/project execution. Monitor this register throughout execution to ensure that the program/project remains on track to deliver the expected benefits. Reflect final measurements in this document at the end of the program/project and use this document during program/project closure to assess program success.

## Benefits Register
Benefit ID | Benefit Title and Description | Requestor | State | Link to Objectives (Project, Business, Strategic) | Owner | Planned Outcome | Stakeholders and Beneficiaries | Program/Project ID and/or Name | Measure Description & Expected Result | Baseline Measure | Measure Frequency | Actual Measures | Status | Expected Realization Date | Actual Realization Date
WCS-01 | Reduce the time needed for document approval | Project Manager | Future | Improve processes and improve organizational connectedness and collaboration. Aligns with innovation strategy of company. | Praveen Yadav | Web-based application that would allow employees to share project documents quickly, and streamline processes like document approval. Employees can easily upload and share documents and receive approvals from the assigned personnel without wasting time in sending email and follow up emails or visiting them in person | All employees, customers who will be impacted by improved company efficiency | Web-Based Collaboration Application | Measurement: Average # of hours between when document is initially submitted and when it is finally approved. Expected Result: Less than 24 hours | Baseline measurement before new system implementation is an average of 4 days | 1 month after go live; bi-weekly after that | N/A | On Track | 2017-12-01 | TBD
WCS-02 | Reduce time needed to complete projects | Project Manager | Future | Improve processes and improve organizational connectedness and collaboration. Aligns with innovation strategy of company. | Praveen Yadav | Web-based application that would allow employees to log in, share project documents quickly, and streamline processes like document approval. Due to the streamlining of process and ease of communication, project teams will complete their work quicker than before | All employees, customers who will be impacted by improved company efficiency | Web-Based Collaboration Application | Measurement: % of projects that are completed on or before schedule. Expected Result: 90% | Baseline measurement: 70% | 1 month after go live; bi-weekly after that | N/A | On Track | 2017-12-01 | TBD
WCS-03 | Improved Net Income due to increased productivity | Project Manager | Future | Improve processes and improve financial bottom line for shareholders | Praveen Yadav | By making communication and document sharing/approval more efficient, productivity will be increased. Projects will be done better, faster, which will ultimately impact the bottom line | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Web-Based Collaboration Application | Measurement: Sales Profit. Expected result: Improvement in sales profit of $15 million in first year, and $20 million in subsequent years | Baseline measurement: Current net income =$5 billion | 1 year after live: quarterly after that | N/A | On Track | 2018-05-02 | TBD
SMS-01 | Increase sales revenue | Project Manager | Future | Improve financial bottom line, benefit shareholders, improve product for customers, and strengthen relations with customers | Dylan Morris | Cars will be more marketable to customers, because this technology will increase fuel efficiency by monitoring and correcting a customer's bad driving habits, reduce maintenance costs, and help customers monitor their driving and their car status more effectively | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Smart Monitoring System | Measurement: Car Sales. Expected Result: Improvement in sales of $210 million annually | Basline measurement: Current sales ($217 billion) | Annually | N/A | On Track | 2018-05-02 | TBD
SMS-02 | Increased customer satisfaction ratings | Project Manager | Future | Improve brand image and brand loyalty, improve financial bottom line, improve product for customers, and strengthen relations with customers, | Dylan Morris | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Smart Monitoring System | Measurement: Customer Satisfaction Rating on scale of 1 to 10. Expected Result: Average Cust. Satisfaction rating of 8 | Baseline measurement: Current average satisfaction rating of 6 | Quarterly | N/A | On Track | 2018-05-03 | TBD
SMS-03 | Increased Fuel Efficiency in cars | Project Manager | Future | Improve product for customers and strengthen relations with customers. Improve customer mobility and vehicle sustainability in keeping with company vision "to be a global leader in sustainable mobility" | Dylan Morris | The Smart Monitoring System will increase a vehicle's fuel efficiency by monitoring the driver's driving habits and correcting them. | Customers who get better technology in their cars that help them save money. Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth. | Smart Monitoring System | Measurement: Fuel Efficiency of cars. Expected Result: 36.5 average MPG (Improvement of 5% on average for each car within 1 year) | Baseline measurement: 35 mpg average | Annually | N/A | On Track | 2018-05-04 | TBD
SMS-04 | Increase # of cars sold | Project Manager | Future | Improve financial bottom line, benefit shareholders, improve product for customers, and strengthen relations with customers | Dylan Morris | Cars will be more marketable to customers, because this technology will increase fuel efficiency by monitoring and correcting a customer's bad driving habits, reduce maintenance costs, and help customers monitor their driving and their car status more effectively | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Smart Monitoring System | Measurement: Car Sales. Expected Result: 11.3 million vehicles sold annually (increase of 1 million cars sold per year) | Basline measurement: Current sales: 10.3 million vehicles | Annually | N/A | On Track | 2018-05-04 | TBD
VRR-01 | Save time and Development costs by allowing changes to be made more quickly as it will enable design teams all over the world to collaborate on ideas more effectively | Project Manager | Future | Improve processes and improve organizational connectedness and collaboration | Palak Gathani | The virtual reality technology will enable designers to design with more freedom and efficiency by allowing changes to be made more quickly | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better cars | Virtual Reality Retail Experience | Measurement: Reduction in development time of 15%, and reductionin development cost of 10% | Baseline measurement: Average Development project time = 2 months, average costs of $2.5 million | Quarterly | N/A | On Track | 2018-07-01 | TBD
VRR-02 | Engineers will be able to create new car designs faster and design car components at a much faster rate | Project Manager | Future | Improve processes and improve organizational connectedness and collaboration | Palak Gathani | The virtual reality technology will enable engineers to work more effectively on creating new car designs as well as designing car components at a much faster rate becaues everything will be done virtually. They will be able to se ethe results of their work immediately. | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better cars | Virtual Reality Retail Experience | Measurement: Time needed to design new components. Expected Result: 30% reduction in time needed for design | Basline Measurement: Average design time: 6 weeks | Quarterly | N/A | On Track | 2018-07-02 | TBD
VRR-03 | Increase sales revenue | Project Manager | Future | Improve financial bottom line, improve product for customers, and strengthen relations with customers | Palak Gathani | VR application will promote better car design, quicker design, will allow customers to virtually examine and test drive cars, and will ultimately lead to improved sales | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better cars | Virtual Reality Retail Experience | Measurement: Car Sales. Expected Result: Improvement in sales of $167 million annually | Basline measurement: Current sales ($217 billion) | Annually | N/A | On Track | 2018-05-02 | TBD
VRR-04 | Decrease cost of infrastructure and maintenance required to build store front. | Project Manager | Future | Improve financial bottom line, improve product for customers, and strengthen relations with customers | Palak Gathani | VR application will promote better car design, quicker design, and will eliminate the need for costly infrastructure because design will be largely virtual - designers will be able to project virtual content onto a physical object and build a virtual car in front of them in minutes | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better cars | Virtual Reality Retail Experience | Measurement: Company expenses on infrastructure: Expected Result: Decrease from $1.6 billion to $1 billion over two years | Baseline measurement: $1.6 billion | Quarterly | N/A | On Track | 2019-05-02 | TBD
VRR-05 | Increased customer reach and customer base | Project Manager | Future | Improve financial bottom line, improve product for customers, and strengthen relations with customers, improve brand image and brand loyalty and ultimately sales | Palak Gathani | VR application willincrease the millennial generation customer reach who are tech savvy, anywhere in the world | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Virtual Reality Retail Experience | Measurement: Number of customers reached. Expected Result: 11.2 million customers | Baseline measurement: 7.3 million customers | Quarterly | N/A | On Track | 2017-05-02 | TBD
VRR-06 | Decrease training cost of employees | Project Manager | Future | Improve financial bottom line, save money that can be reinvested to better the company in R&D, marketing, etc. Increase employee satisfaction and productivity as well | Palak Gathani | VR application will decrease cost of training employees because It will decrease training costs of employees by at least 10% who work directly on designing and assembling parts. When the employees use virtual parts to build a car, miscellaneous expenses incurred for using actual parts for building cars for training purposes shall cease to exist. | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Virtual Reality Retail Experience | Measurement: Average cost of training employees who work on design and assembly. Expected Result: $1,688 | Baseline measurement: Average cost of training employees currently: $2,394 | Quarterly | N/A | On Track | 2017-09-02 | TBD
VRR-07 | Increased customer interaction | Project Manager | Future | Improve customer outreach, strengthen relationships with clients, grow customer base | Palak Gathani | Customers will be able to build their personalized auto model without having to go to the store, which will increase customer interaction by at least 20% | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Virtual Reality Retail Experience | Measurement: Customer interaction will increase by 20% | Baseline: 20,387 hours of customer interaction annually | Twice per year | N/A | On Track | 2017-11-02 | TBD
VRR-08 | Decreased time-to-market | Project Manager | Future | Improve processes, save costs and improve bottom line, strengthen relationships with customers by giving them products faster | Palak Gathani | Time to market for newly conceptualized and designed models will decrease significantly which will help the company react quickly to market changes and demands | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better cars | Virtual Reality Retail Experience | Measurement: Average time to market for new models: Expected result: 3 months | Baseline: Time to market is currently at an average of 5 months | 1 year after live: quarterly after that | N/A | On Track | 2018-05-02 | TBD
BCI-01 | Increase market share | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers | Alessandro Vomero | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, customers who get better technology in their cars that help them save money | Brain Computer Interface | Measurement: Market Share %: Expected Result: 14% | Baseline measurement: 13.55% | Every 6 months after going live | N/A | On Track | 2018-05-02 | TBD
BCI-02 | Increase in Product Portfolio | Project Manager | Future | Improve options for customers, have more diverse product-base to ensure that we are global leaders in sustainable mobility, increase market saturation. Strengthen innovation power and build mobility solutions | Alessandro Vomero | Volkswagen currently has 12 independent brands with an individual identity and a common goal - mobility. Brands range from motorcycles to luxury vehicles. This technology will allow Volkswagen to produce more products, branch out into more brands, and provide our customers with even more great products | Shareholders who own stock in the company, customers who get better cars and more options, C-level employees and regular employees who will benefit from increased market saturation and growth of company | Brain Computer Interface | Measurement: # of brands in portfolio: Expected Result: 15 brands | Baseline Measurement: 12 brands | 1 year after live: annually | N/A | On Track | 2018-05-02 | TBD
BCI-03 | Reduction of Car accidents | Project Manager | Future | Social Benefit. Improve sustainable mobility for customers and provide a social benefit. Improve brand image and positive customer associations with brand | Alessandro Vomero | The BCI technology will be able to reduce the # of accidents by predicting them moments before they occur based on input from driver's brain and impelling the car to take evasive action | Social Benefit. Customers will benefit, and society at large. Will save many lives. Managers, C-level employees, and shareholders will benefit from improvement in brand image | Brain Computer Interface | Measurement: # of yearly deaths from auto accidents in the US. Expected Result: 25,000 | Baseline Measurement: 30,000 | 1 year after live: annually | N/A | On Track | 2018-05-02 | TBD
ARD-01 | Increase in Sales | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers | Michael Lynch | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Augmented Reality Dashboard | Measurement: Sales revenue. Expected result: $230 billion | Baseline: $217 billion | 1 year after live: quarterly after that | N/A | On Track | 2018-05-02 | TBD
ARD-02 | Increase in market share | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers | Michael Lynch | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Augmented Reality Dashboard | Measurement: Market Share %: Expected Result: 14% | Baseline measurement: 13.55% | 1 year after live: quarterly after that | N/A | On Track | 2018-05-02 | TBD
ARD-03 | Increase in positive brand recognition | Project Manager | Future | Improve financial bottom line, strengthen relations with customers, improve brand image and brand loyalty | Michael Lynch | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction and better brand recognition | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Augmented Reality Dashboard | Measurement: Ratings of brand opinion on scale of 1 to 10. Expected result: 8.5 | Baseline measurement: Current ratings: 6.5 | 6 months after live: quarterly after that | N/A | On Track | 2017-11-02 | TBD
ARD-04 | Increased customer reach and customer base | Project Manager | Future | Improve financial bottom line, improve product for customers, and strengthen relations with customers, improve brand image and brand loyalty and ultimately sales | Michael Lynch | Augmented reality dashboards will be attractive to the millennial generation customer reach who are tech savvy, and to other generations as well, and will increase our customer base | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Augmented Reality Dashboard | Measurement: Number of customers reached. Expected Result: 15 million customers | Baseline measurement: 10.3 million customers | Quarterly | N/A | On Track | 2017-05-02 | TBD
3DP-01 | Increase sales of vehicles | Project Manager | Future | Improve financial bottom line, improve product for customers, and strengthen relations with customers, improve brand image and brand loyalty and ultimately sales | James Kelly | Increase sales of vehicles overall based on better repair and maintenance, better customer service and lower maintenance costs to customers, enticing them to buy | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | 3D Parts Printing | Measurement: Car Sales. Expected Result: 14.9 million vehicles sold annually | Basline measurement: Current sales: 10.3 million vehicles | Annually | N/A | On Track | 2018-05-02 | TBD
3DP-02 | Decrease of Inventory Carrying Costs | Project Manager | Future | Improve financial bottom line, improve processes and eliminate waste, increase productivity | James Kelly | 3D Parts division will offer an ultimate version of just in time inventory, which will cut down on inventory carrying costs. Custom 3D printers will be able to print inventory parts as they are needed, and in a timely fashion | All employees, customers who will be impacted by improved company efficiency, reduced costs, and better company financial health | 3D Parts Printing | Measurements: Inventory Carrying Costs: Expected Result: $138 million | Baseline measurement: $213 million | Annually | N/A | On Track | 2018-05-02 | TBD
3DP-03 | Decrease of Raw Materials Costs, specifically waste | Project Manager | Future | Improve financial bottom line, improve processes and eliminate waste, increase productivity | James Kelly | Customer 3D printers will be able to take advantage of exact amounts of materials to be used in manucaturing parts | All employees, customers who will be impacted by improved company efficiency, reduced costs, and better company financial health. Also customers who will be impacted by improved company functioning | 3D Parts Printing | Measrement: Raw Materials Expenses. Expected Result: $94 million | Baseline Measurement: $ 154 million | Quarterly | N/A | On Track | 2017-05-02 | TBD
3DP-04 | Decrease of shipping costs for parts | Project Manager | Future | Improve financial bottom line, improve processes and eliminate waste, increase productivity | James Kelly | Customer 3D printers will be able to take advantage of exact amounts of materials to be used in manucaturing parts and the shipping of raw materials or local sourcing of materials for each of the printing locations | All employees, customers who will be impacted by improved company efficiency, reduced costs, and better company financial health. Also customers who will be impacted by improved company functioning | 3D Parts Printing | Measrement: Shipping Expenses for Parts. Expected Result: $47 million | Baseline Measurement: $ 64 million | Quarterly | N/A | On Track | 2017-05-02 | TBD
3DP-05 | Positive ROI over a 10-20 year period on R&D expenditures | Project Manager | Future | Improve financial bottom line, improve processes and eliminate waste, increase productivity | James Kelly | 3D printing technology is expected to save the company money over time on inventory carrying costs, raw materials, and shipping, as well as leading to increased sales. The project will make the company more efficient cash and operations wise and re-create the brand as a high-tech car manufacturer | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | 3D Parts Printing | Measurement: ROI on R&D Expenditures. Expected Result: 12% Positive ROI | Basline Measurement: N/A | Annually | N/A | On Track | 2030-05-02 | TBD
AI-01 | Reduction in total operating expenses | Project Manager | Future | Improve financial bottom line, improve processes and eliminate waste, increase energy efficiency and quality, reduce total cost of ownership | Lee Parker | AI will be a component off effective energy conservation initiatives such as automated resource and energy distribution management, leading to lower cost of ownership | Managers, C-level employees, other shareholders, including regular employees who may benefit from increased company savings | Artificial Intelligence | Measurement: Total Annual Operating Expenses. Expected Result: $205 Billion | Baseline Measurement: $211 billion | Annually | $211 billion | On Track | 2021-01-02 | TBD
AI-02 | Increased car sales | Project Manager | Future | Improve financial bottom line, strengthen relations with customers, improve brand image and brand loyalty | Lee Parker | AI will be a highly marketable feature that customers will be interested in, so being the first to market with real AI in cars will ensure a growth in sales and customer base | Managers, C-level employees, other shareholders, and customers | Artificial Intelligence | Measurement: Car Sales. Expected Result: 15.2 million vehicles sold annually | Basline measurement: Current sales: 10.3 million vehicles | 3 months after live: quarterly after that | 10.3 million vehicles | On Track | 2021-01-02 | TBD
AI-03 | Increased Sales Revenue | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers, improve brand image | Lee Parker | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customers who get better technology in their cars that help them save money | Artificial Intelligence | Measurement: Sales revenue. Expected result: $237 billion | Baseline: $217 billion | 3 months after live: quarterly after that | N/A | On Track | 2021-01-02 | TBD
AI-04 | Increased Operating Profit Margin | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers, improve brand image | Lee Parker | Cars will be more marketable to customers, and will provide a better driving experience, leading to increased customer satisfaction | Shareholders who own stock in the company, employees due to increased company performance leading to potential improved salaries and growth, and customer who benefit from a financially healthy company | Artificial Intelligence | Measurement: Profit Margin. Expected Result: 8.7% | Baseline: Profit Margin of 5.3% | Annually starting 1 year after it goes live | N/A | On Track | 2021-01-02 | TBD
AI-05 | Positive ROI over a 5-10 year period in the Automotive Division | Project Manager | Future | Improve financial bottom line, improve product for customers, benefit stakeholders and strengthen relations with customers, improve brand image | Lee Parker | The investment required to get this technology off the ground will net a positive return on investment by reducing future operating expenses and increasing sales, profit, and customer base | Employees, shareholders, and customers who wlil reap the rewards in the form of better future products due to the company having more profit to reinvest and better iteself | Artificial Intelligence | Measurement: ROI in Automotive Division. Expected Result: 9% Positive ROI | Basline Measurement: N/A | Annually starting 1 year after it goes live | N/A | On Track | 2021-01-02 | TBD
Note on A1: Salonen, Deb: Sequential numbering in the format BEN-###.
Note on B1: Salonen, Deb: A description of the desired benefit, including a title, current and target state/measurement
Note on C1: Salonen, Deb: The individual that raised the benefit for inclusion as part of the Program.
Note on D1: Salonen, Deb: hat state is the benefit o Active o Future
Note on E1: Salonen, Deb: Document which University or IT Strategy/Strategies this benefit aligns to, and how
Note on F1: Salonen, Deb: The individual responsible for measuring benefit progress, and accomplishing the benefit objective.
Note on G1: Salonen, Deb: What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”)
Note on H1: Salonen, Deb: Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Note on I1: Salonen, Deb: The ID (from the Portfolio list) and name of the project(s) or initiative(s) within the Program that will deliver the Planned Outcome.
Note on J1: Salonen, Deb: What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Note on K1: Salonen, Deb: What was the value of the measure before work started?
Note on L1: Salonen, Deb: How often will a progress measurement take place?
Note on M1: Salonen, Deb: What was the latest progress measurement?
Note on N1: Salonen, Deb: High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o On Track = On Schedule, Budget and Scope o Warning = Significant risk to Schedule, Budget and/or Scope o Critical = Schedule, Budget and/or Scope will not be met o Realized = Benefit realized o NOT Realized = Decision made that benefit will not be realized

## Definitions & Values
Benefit Register Definitions and Values
Benefit ID – A unique identifer or number for each benefit entered | Measure Description & Expected Result – What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Benefit Title and Description – A title and brief description of the desired benefit | Baseline Measure – What was the value of the measure before work started?
Requestor – The individual or stakeholder group that raised the benefit for inclusion. | Measure Frequency – How often will a progress measurement take place?
State - State of current benefit. o Active = Benefit is currently active o Future = Benefit is identified for the future | Actual Measures – What are the actual measurement results and the date taken?
Link to Business Objectives – Document or link to University, departmental, or IT strategies this benefit aligns to, and how | Status – High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o Realized = Benefit has been realized. Actual result matches expected. o On Track = On Schedule for realizing benefit. o Warning = Some risk towards realizing benefit. o Critical = Benefit realization will not be met.
Owner – The individual responsible for measuring benefit progress, and accomplishing the benefit objective. | Expected Realization Date – Year and month originally planned for completion of Planned Outcome.
Planned Outcome – What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”) | Actual Realization Date – Date of completion of the Planned Outcome/Benefit. If the full benefit is no longer expected, enter N/A
Stakeholders and Beneficiaries – Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Program/Project ID and Name – The ID and/or name of the program, project(s), or initiative(s) that will deliver the Planned Outcome

## Sheet1 (hidden)
Active
Future
Realized
On Track
Warning
Critical