## Sheet1
This log contains risks across all projects of the portfolio, and contains project specific risks, and overall portfolio risks including joint project risks.
Projects: AI - Artificial Intelligence ARD - Augmented Reality Dashboard BCI - Brain-Computer Interface SMS - Smart Monitoring System VRR - Virtual Reality Retail WCS - Web-based Collaboration System 3DP - 3-D Printing
1. BASIC RISK INFORMATION | [6 empty] | 2. RISK ASSESSMENT INFORMATION | [7 empty] | 3. RISK RESPONSE INFORMATION
Risk Number | Risk Description / Risk Event Statement | Corresponding Assumption Register | Risk Category/Source | Responsible | Date Reported day-month-year | Last Update day-month-year | Impact H / M / L | Impact Score | Impact Description | Probability H / M / L | Probability Score | Risk Score | Timeline N/M/F | Status of Response N / P / PE / EE | Completed Actions | Planned Future Actions | Trigger | Risk Status Open / Closed / Moved to Issue
AI-01 | If funding is not available, or reduced for any reason, and project resources are reduced, the project will be delayed or cancelled. | 8 | Budget/Funding | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | Project budget will be impacted. Schedule will increase, possible impact to technical performance due to loss of personnel. | L | 2 | 10 | M | N |  |  | Projected budget shows funding decrease >= 5% | Open
AI-02 | If project is not completed in time, will impact schedule for first major market offering of self-driving vehicle in 2022 | 9 | Schedule | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | AI technology will not be available for integration into self-driving vehicle system. | H | 5 | 20 | M | N |  | Conduct baseline review (EVM) quarterly. | SPI < 95% | Open
AI-03 | Technical difficulties in AI development or implementation will delay planned project outcome. | 10 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | Technical risk could originate from difficulties in integration with other required mobility technologies for self-driving vehicles | H | 5 | 25 | M | N |  | Conduct technical review quarterly. | Technical reviews reveal progress on Key Technical Measurements at < 90% | Open
AI-04 | Changes in safety, vehicle, traffic regulations will affect project requirements. | 11 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | H | 4 | Changes in project requirements due to regulation will increase technical complexity, and cause cost and schedule to increase. | H | 4 | 16 | M | N |  |  | Legislation is proposed. | Open
AI-05 | AI failures could contribute or cause vehicle accidents. | 2012-01-04 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Failure of the technology could cause improper and unsafe control of the vehicle, leading to accidents. | M | 3 | 15 | L | N |  | Conduct technical review quarterly. | Testing shows failure rate below objectives and close to thresholds. | Open
AI-06 | Cyberattacks could compromise AI system. | 13 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Cyberattacks could compromise AI system and cause accidents. | M | 3 | 15 | L | N |  |  | Cyber scans show vulnerabilities. | Open
AI-07 | Availability of tools and equipment | 2 | Resources | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | Lack of proper resources - labs, tools, equipment will delay project or render the project unexecutable | L | 1 | 5 | N | N |  | Conduct resource planning with portfolio management | Project resources are diverted or project funding is impacted by loss of >=5% | Open
AI-08 | Integration with other vehicle technologies and components | 3 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | If integration with other vehicle components and technologies does not occur in the right sequences or is unsucessful, then project benefits will be delayed or not realized. | M | 3 | 15 | N | N |  |  | Integration and testing is delayed, causing SPI impact of minus 5% or more. | Open
SMS-01 | Automobiles connected to internet will be vulnerable to cyberattacks. | 70 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Cyberattacks could compromise driver control and cause accidents. | M | 3 | 15 | L | N |  |  | Cyber scans show vulnerabilities. | Open
SMS-02 | Automobiles connected to the internet will be a source of potential loss of customer information privacy | 70 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | Cyberattacks would compromise customer privacy due to leakage of information connected with vehicle ownership. | M | 3 | 12 | L | N |  |  | Cyber scans show vulnerabilities. | Open
SMS-03 | The technology may engender a false sense of security regarding driving patterns. | 61 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | Overreliance on driver aids could increase risk of vehicle accidents. | L | 2 | 6 | L | N |  |  | Test groups demonstrate reduced reaction time. | Open
SMS-04 | Fossil fuel use and viability of benefit | 58, 59, 60 | Environment | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | As automobiles move away from fossile fuel use, the ROI on the benefit will be reduced. | L | 2 | 6 | L | N |  | Conduct economic study on long term use of fossil fuels. Hire consulting firm. | Study indicates regulatory and economic impacts likely to reduce fossil fuel use by greater than 30% above expected decline over 10 year period. | Open
SMS-05 | Customer adoption and use of technology. | 65, 66, 67,68,69 | Environment | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | If customer use is low, and/or technology does not improve vehicle maitenance cycle time or reduce costs, then benefit will not have been realized and resources have been wasted. | M | 3 | 9 |  |  |  |  | Analyis indicates low usage or no change in maintenance statistics (mean time between repairs, etc) | Open
AI/SMS-01 | These technologies could be seen as partially competing with each other. |  | Budget/Funding, Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | Strategies may not be aligned between the two projects. Projects could be misprioritized and resources could be misallocated. | L | 2 | 6 | N | N |  | Joint technical reviews of both projects to determine synergies, competing interests and outcomes, priorities, and resource allocation. | Joint technical review comparing cost, schedule, and technical performance. | Open
WCS-01 | System vulnerability to cyberattacks. |  | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | L | 2 | Company documents could be compromised, leak of proprietary information. | L | 1 | 2 | L | N |  |  | Cyber scans show vulnerabilities. | Open
WCS-02 | Internal loss of workflow control | 77, 78 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | L | 1 | Improper permissions or compromised workflow could decrease productivity, cause negative impacts to project schedules. | L | 1 | 1 | L | N |  |  | Testing shows problem is likely (>10%) to occur. | Open
WCS-03 | Ineffective employee training. | 76 | Technical | Project Manager | 2017-05-01 | 5/1/12017 | L | 2 | Inadequate training could impact proper employee use of new systemew system and cause disruption in projects. | L | 2 | 4 | L | N |  | Conduct developmental testing. | Testing shows problem is likely (>10%) to occur. | Open
WCS-04 | Employees do not adopt the new system | 75 | Schedule | Portfolio Manager | 2017-05-01 | 5/1/12017 | M | 3 | Delays in adoption by employees will waste resources and could contribute to project delays. | M | 3 | 9 | L | N |  | Conduct market survey after 3 months of operation | Adoption rate is less than 50% after 3 months in operation. | Open
WCS-05 | System does not improve, and possibly hinders, productivity. | 79 | Technical | Portfolio Manager | 2017-05-01 | 5/1/12017 | M | 3 | If system requirements are not properly defined and implemented, productivity could decrease. | L | 2 | 6 | L | N |  |  | Testing shows problem is likely (>10%) to occur. Adoption rate is less than 50% after 3 months in operation. | Open
3DP-01 | Technology not able to produce parts up to safety standards. | 19 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | Inferior parts could lead to parts failure, which in turn reduces vehicle safety and could cause accidents. | M | 3 | 12 | L | N |  | Conduct technical review quarterly. | Safety and reliability tests show failure rate greater than 1% variance from specified standards. | Open
3DP-02 | Technology/printer is too expensive. | 20 | Cost | Project Manager | 2017-05-01 | 5/1/12017 | H | 4 | Due to high cost of technology, benefit of reduced inventory and shipping costs cannot be realized. | M | 3 | 12 | M | N |  |  | Cost benefit analysis shows negative return at first project technical review. | Open
3DP-03 | Lack of quality in printed parts. | 21 | Cost | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Degraded parts quality increases vehicle reliability and increases downtime, harming company reputation and increasing warranty costs. | M | 3 | 15 | L | N |  |  | Cost benefit analysis using calculated failure rates compared to normal manufactured parts. | Open
3DP-04 | Lower speed to market/competition. | 22 | Schedule | Project Manager | 2017-05-01 | 2017-05-01 | M | 3 | If competitors bring the concept to market first, it could result in loss of market share as customers adopt the new technology. | H | 4 | 12 | L | N |  |  | SPI < 95% | Open
3DP-05 | Regulatory standards | 14 | Technical, Schedule | Project Manager | 2017-05-01 | 2017-05-01 | M | 3 | Changes in government regulation for standards for use of 3D parts in cars will affect development and implementation timeframes | M | 3 | 9 | M | N |  |  | Change in government regulation. | Open
3DP-06 | Consumer acceptance and brand image | 16, 17 | Marketing/Sales | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | If consumers do not accept or are extremly slow to accept 3D printed parts, then sales and brand image will be negatively impacted. | M | 3 | 12 | L | N |  | Conduct focus group studies. | Preliminary market survey and focus group studies indicate acceptance rate below 75% | Open
3DP-07 | Inventory management with Just-in-Time | 18 | Cost | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | If JIT inventory benefit is not realized, then regular supply and inventory system will have to be continued. | L | 2 | 6 | L | N |  | Conduct supply chain analysis | Supply chain analysis indicates benefit not likely (<50%) | Open
BCI-01 | Extreme "bleeding edge" of biocomputer technology. | 31, 32 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Technology may be so advanced as be impractical to implement effectively and safely at this point in time. | H | 5 | 25 | N | N |  | Hire consulting firm to conduct technology feasibility study. | Technology feasibility study indicates technical infeasibiity. | Open
BCI-02 | Resources required to develop. | 32, 34 | Cost | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Sufficient resources may not be available to devote when compared with other projects that are more immediately feasible. | H | 5 | 25 | N | N |  | Hire consulting firm to conduct independent cost estimate. | Cost estimate indicates unnaffordable. | Open
BCI-03 | Timeline to develop. |  | Schedule | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Timeline to develop technology may prove impractical to VW's 2025 strategy. | H | 5 | 25 | N | N |  |  | Use outsourced studies to determine schedule. | Open
BCI-04 | Public adoption of technology and implant. | 31 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Public may not adopt the technology and implant as safe or desirable. Resources would be wasted. | H | 5 | 25 | L | N |  | Hire consulting firm to conduct market survey, focus group study. | Study indicates no/low adoption rate among likely consumers. | Open
BCI-05 | Technical difficulties in neural/computer interface development or implementation will delay planned project outcome. |  | Technical | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | Technical risk could originate from difficulties in integration with other required mobility technologies for self-driving vehicles | H | 5 | 25 | M | N |  |  | Technical reviews reveal progress on Key Technical Measurements at < 90% | Open
BCI-06 | Partnership with other research organizations | 35 | Resources, Technical | Project Manager | 2017-05-01 | 2017-05-01 | H | 5 | If VW cannont leverage the bio-tech partnerships necessary to bring this technology to the market, then benefit is not feasible. | H | 4 | 20 | N | N |  | Portfolio management reach out to industry and academia to create partnerships. | Parnerships are not in place before development is scheduled to begin. | Open
BCI-07 | Corporate security for proprietary information | 33 | Security | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | Data leakage could cause loss of competitive advantage, or negative PR. | H | 4 | 16 | N | N |  | Conduct cybersecurity review of project. | Cybersecurity review reveals vulnerabilities that estimate chance of hacking at >=1% | Open
AI/BCI-01 | These technologies could be seen as directly competing with each other. |  | Budget/Funding, Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Strategies may not be aligned between the two projects. Projects could be misprioritized and resources could be misallocated. | H | 5 | 25 | N | N |  | Joint technical reviews of both projects to determine synergies, competing interests and outcomes, priorities, and resource allocation. | Joint technical review comparing cost, schedule, and technical performance. | Open
VRR-01 | Available market VR technology to meet project requirements. | 52 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | M | 3 | Market technology may not be sufficiently advanced to meet project requirements. | M | 3 | 9 | M | N |  | Conduct technology assessment. | Assessment indicates key technology components are not available or suitable. | Open
VRR-02 | Cyberattacks could compromise VR system. | 53 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | Cyberattacks could compromise the system and decrease usefulness, particularly amont designers and engineers. | M | 3 | 9 | M | N |  |  | Cyber scans show vulnerabilities. | Open
VRR-03 | Non-availability to customers | 50, 54 | Cost | Portfolio Manager | 2017-05-01 | 2017-05-01 | L | 1 | Large portions of the customer base will likely not have VR headsets to make use of the VR service, and will have to go to dealerships. | H | 5 | 5 | M | N |  | Conduct market survey. | Survey shows technology will not be readily available to likely consumers. | Open
VRR-04 | Non-usefulness to customers | 50, 51, 55 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | L | 1 | If VR service does not meet needs of customers, project benefit will not be realized, wasted resources. | M | 3 | 3 | M | N |  | Conduct focus group study. | Study indicates no/low adoption rate among likely consumers. | Open
VRR-05 | Negative customer experience. | 51, 56 | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | Negative customer experience will adversely affect sales. | L | 2 | 8 | M | N |  | Conduct focus group study. | Study indicates neutral or negative reaction among likely consumers. | Open
VRR-06 | Technical challenges for internal employees. | 57 | Technical | Project Manager | 2017-05-01 | 2017-05-01 | L | 1 | If the technology proves too difficult to use, or is unrealialbe, then product will not be used. | M | 3 | 3 | M | N |  | Conduct employee focus group study. | Study indicates problems likely. Market acceptance < 75% | Open
ARD-01 | Human System's Engineering. Dashboard design related to driver safety. |  | Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | The dashboard projection, if improperly designed, may prove a distraction for drivers and increase accident rate. | M | 3 | 15 | M | N |  |  | Results of testing indicate dashboard hinders safe driving conditions. Calculated contribution to risk of accident 1% or greater. | Open
ARD-02 | Technical difficulties in development or implementation will delay planned project outcome. |  | Technical | Project Manager | 2017-05-01 | 2017-05-01 | M | 3 | Technical difficulties will delay product offering. | M | 3 | 9 | N | N |  |  | Technical reviews reveal progress on Key Technical Measurements at < 90% | Open
ARD-03 | If funding is not available, or reduced for any reason, and project resources are reduced, the project will be delayed or cancelled. |  | Budget/Funding | Project Manager | 2017-05-01 | 2017-05-01 | H | 4 | Project budget will be impacted. Schedule will increase, possible impact to technical performance due to loss of personnel. | L | 1 | 4 | N | N |  |  | Projected budget shows funding decrease >= 5% | Open
ARD-04 | Market acceptance. | 41 | Marketing/Sales | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 4 | Poor market acceptance, or negative customer experience with the technology will adversely affect sales. | L | 2 | 8 | L | N |  | Conduct employee focus group study. | Study indicates problems likely. Market acceptance < 75% | Open
ARD-05 | Speed to market. | 42 | Schedule | Portfolio Manager | 2017-05-01 | 2017-05-01 | M | 3 | Not leading the market with the technology will result in lower ROI than expected for the benefit. | M | 3 | 9 | M | N |  |  | Project SPI <95% | Open
ARD/BCI-01 | These technologies could be seen as directly competing with each other. |  | Budget/Funding, Technical | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Strategies may not be aligned between the two projects. Projects could be misprioritized and resources could be misallocated. | H | 5 | 25 | N | N |  | Joint technical reviews of both projects to determine synergies, competing interests and outcomes, priorities, and resource allocation. | Joint technical review comparing cost, schedule, and technical performance. | Open
Portfolio-1 | Loss of development facilities. |  | Acts of God | Portfolio Manager | 2017-05-01 | 2017-05-01 | H | 5 | Loss of development facilities, resources due to fire, flood, other disasters will delay projects indefinately. | L | 1 | 5 | N | N |  | Develop Continuity of Operations Plan (COOP). Purchase insurance. | Portfolio manager conduct review with corporate management to determine requirements for COOP and review insurance policies. | Open